

**1st Quarterly Report**

January –March 2014

Prepared by Ms. Bun Rathana

Checked by Mr. PhengSaochheng and Ms. Map Somaya

June 2014

# MITH SAMLANH WOULD LIKE TO THANK ITS SPONSORS:

* ***ACTED-PSF, AusAID/CDF, AusAID/HAARP, DAK Foundation, Dayer& Ahlstrom, Child Wise Cambodia, Deutsche Bank, Dan Church Aid/ChristianAid, European Union, EZECOM, Evert en Gisela BoudewijnStichting, Inditex/Friends-Deutschland, Friends-International, Global Fund, Give2Asia, Juniclair, ,La Chaine de L’Espoir, Planet Wheeler, Phnom Penh Capital Hall, Riverview Children Foundation, Secours Catholique/Reseaumondial Caritas, SNV Netherland Development Organization, Sipar/AFD, The Mercury Phoenix Trust, The Work Together Foundation (Smile Together Partnership), UNICEF, USAID, World Childhood Foundation and World Education.***

# ABOUT MITH SAMLANH

**ORGANIZATION BACKGROUND**

Mith Samlanh was established in August 1994 and is a Cambodian led non-government organization committed to working with marginalized Cambodian children and youth, their families and communities. Mith Samlanh was formally registered as a local Cambodian NGO in 2002.Every year, Mith Samlanh provides various outreach programs, vocational training, education, counselling, food, shelter, medical services and income generation programs to 15,000 marginalized children, youth and families in Phnom Penh.

**VISION**

Together, we protect marginalized children/youth and related groups and with them create innovative and exciting opportunities to build their futures.

**MISSION**

Mith Samlanh is a local non Governmental organization, founded by Friends-International and a member of the CYTI Alliance, which works with and for marginalized children, youth, their families and their communities to build their futures.

* **Protecting**marginalized children and youth from all forms of abuse within the scope of the International Convention of the Rights of the Child;
* **Reintegrating** marginalized children and youth so they become actively involved in the development of their society;
* **Preventing** marginalized children and youth from engaging in risky behaviour and/or dangerous situations that compromise their futures;
* **Improving**the way organizations work by promoting innovative and effective approaches with the active participation of the children and youth;
* **Influencing**all tiers of society to provide supportive environments and adopt positive behaviour changes.

**CORE VALUES**

* Child value and best interest
* Transparency
* Sustainability
* Positive approach

**OVERVIEW**

Mith Samlanh currently implements sevenmain programs: protection/outreach; youth empowerment; education; vocational training and employment; family reintegration and alternative care; family income generation; and social business. This work is supported by six specialists (child protection, medical, case management, drugs, lifeskills, ChildSafe) and a senior management team, finance team, admin/HR team and M&E team.

# GLOSSARY

|  |  |
| --- | --- |
| ARV | Antiretroviral |
| CC | Correction Center |
| CCWC | [Commune Committee for Women and Children](http://gbv.open.org.kh/reports/view/300?l=km&l=en_US) |
| DoSVY | Department of Social Affair Veteran and Youth Rehabilitation |
| FSB | Friends Social Business |
| FI | Friends-International |
| HBP | Home Based Production |
| HIV/AIDS | Human Immunodeficiency Virus/ Acquired Immune Deficiency Syndrome |
| IEC | Information, Education and Communication |
| ITP | Individual Training Plans |
| KPMG | Klynveld Peat MartwickGoerdeler |
| MoU | [Memorandum of understanding](http://en.wikipedia.org/wiki/Memorandum_of_understanding) |
| MER | Monitoring, Evaluation and Research |
| MoSVY | Ministry of Social Affair Veteran and Youth Rehabilitation |
| MS | Mith Samlanh |
| NACD | [National Authority for Combating Drugs](http://www.nacd.gov.kh/) |
| NGO GPP | NGO Governance & Professional Practice |
| NFE | Non-Formal Education |
| NCHAD | The National Centre for HIV/AIDS Dermatology and STDs |
| PMTCT | Preventing mother to child transmission |
| STDs | Sexually Transmitted Diseases |
| SOP | [Standard Operating Procedure](http://www.extension.iastate.edu/foodsafety/toolkit/communication/OverviewofSOPs.pdf) |
| TH | Transitional Home |
| VCCT | Voluntary Confidential Counselling and Testing |
|  |  |
|  |  |

# MITH SAMLANH’S ACHIEVEMENT 2014: January to March

* 5,947 (F: 2,332) children and youth and 2,955 (F: 1,630)caretakers received services in Phnom Penh and Provinces since 1st January 2014.
* 398,743 (F: 139,792) services were provided to children, youth and their caretakers this quarter
* 91 (F: 26) children and youth were supported to move away from street life since 1st January 2014.
* 144 (F: 61) children received remedial education since 1st January 2014.
* 01 (F: 0) new child was supported to reintegrate into public school
* 1,382 (F: 597) children received support to remain in public school through follow up in Phnom Penh and Provinces since 1st January 2014,
* and 460 (F: 197) children stop to support because they are successfully supported by their families.
* 308(F: 87) youth received vocational training since 1st January 2014.
* 31(F: 07) youth were placed into employment (employment, self-employment, directly into employment and find job by themselves) in Phnom Penh and Provinces since 1st January 2014.
* 214 (F: 54) children/youth children and youth accessed safe lodging facilities in 3 Transitional Homes (THs) since 1st January 2014.
* 39(F: 08) children and youth were reintegrated into family environment (direct, extended, foster care, independent living and group living) in Phnom Penh and Provinces since 1st January 2014.
* 153caretakers received support for income generation activities (Small business and HBP) since 1st January 2014.
* 736 (F: 171) ChildSafe Members including 228 (F: 169) ChildSafe community members are active in Phnom Penh.

|  |  |  |
| --- | --- | --- |
| **NTERVENTION LOGIC** | **KEY PERFORMANCE INDICATOR** | **RESULT** |
| 1. **Best Practice:** Mith Samlanh is recognized as international best practice program | | |
| * 1. **Management is best practice and provides strategic guidance and effective support to the programs** | **Management:**   * Relevant MoUs with government are signed or renewed * Representation with donors, government and partners is effective and transparent * Relationship with the Board is effective * Finalise new MS Statutes and IR for Board and hire new board members   **Structure:**   * MS structure is adapted to the external and internal needs and changes to remain efficient and responsive * Continue and consolidate team restructure in outskirts zones and central Phnom Penh * Plan for building on MS land is developed   **Communications/Fundraising:**   * MithSamlanh’s internal and external communication is efficient, updated and the profile is constantly improved * Implement fundraising events and communication materials including for 20th anniversary * Secure donor funding to improve funding situation | **Management:**   * Mith Samlanh has signed a three year MoU with Ministry of Education, Youth and Sport on 28th February 2014, covering 2014 to 2016. * Mith Samlanh will sign a MoU with Phnom Penh Municipality in the next quarter. * This quarter, various donors such as Unicef, Wise, USAID (Ambassador), La Chaine de L’Espoir, Riverview and Planet Wheeler came to visit Mith Samlanh program through Friends-International. * The board meeting was conducted in March 2014 to present the 2013 achievements and approve the strategic plan and budget for 2014 and discuss plans to recruit two new board members.   **Structure:**   * The new structure is in place for Andong and ChbarAmpov teams and team restructure and mapping of central Phnom Penh is underway.   **Communications/Fundraising:**   * Mith Samlanh’s brochure has been translated into Khmer version. * The acoustic picnic fundraising event took place at Mith Samlanh Center on 8th February 2014. * Mith Samlanh team had a meeting to plan for the Mith Samlanh Staff party and 20th anniversary events. * Secured follow on funding from Evert&Gisela and DFAT (previously AusAID) and from new donors Tesco and Comic Relief. |
| 1. **Admin/HR ,Finance and M&E :**Admin/HR ,Finance and M&E are best practice and providing effective support to the programs | | |
| * 1. **The HR SoPs and MS IR are implemented** | **Admin&Human Resource:**   * Adapt SoPs for Human Resource with FI * Update MS Internal Regulation (corruption/family, conflict of interest, bonus, etc.) in line with new finance policy * Training, induction and ITPs in place for all staff * Build middle management capacity and develop career path and internal promotion within each team | **Admin&Human Resource:**   * The internal rules have been updated and implemented in collaboration with Friends-International. * 24 (F: 06) new staff were recruited based on recruitment guidelines to fill vacancies, including 03 (F: 2) volunteers and 02(F: 01) staff were promoted and received an orientation/induction on the MS Internal Regulations/Procedures regarding: * MS Internal Regulations and Structure * Gender Equality Policy * Code of Conduct/Child Protection Policy * Procurement and Conflict of Interest * Bribe and Gifts Policy * Mith Samlanh Program * 134 (F: 87) staff received 196 sessions of internal and external training such as English, Program Evaluation, Fraud Awareness, Drug Data Collection, IPSS,​Basic Orientation, Positive Power and Influence organized by MS, FI and outside institutions, including ACE, Australian Embassy, and Khemerak University. * This quarter, the human resource information management system recorded: * 264 (F: 111) Mith Samlanh staff including 03(F: 02) volunteer staff and 24(F: 06) new staff. * 11(F: 03) staff ended their contracts including 05 resignations, 05 immediate terminations and 1 staff quit their job. |
| * 1. **ThefinanceSoP and Policy are implemented** | **Finance:**   * Admin & Finance Policy & Procedures Manual updated as and when needed. * All staff are supported to follow Finance & Admin Policy & Procedures * Handbook for non-finance staff to follow Finance Policy * All Internal reports and donor reports are completed and delivered on a timely basis. * All internal business reports are completed and delivered on a timely basis. * The external audits show quality financial systems. * The internal control is strengthening the whole operation of Mith Samlanh. * List of fixed assets is updated, counted and checked quarterly/ biannually. * Finance staffs are trained and ongoing technical support is provided by Friends-International * Annual Budget is prepared and updated on a timely basis * The financial report will present to all senior MS program staff for openness and transparency every quarter meeting * Annual financial and Audit reports are shared publicly on the MS website | **Finance:**   * The user-friendly finance policy and procedure Manual was reviewed by Technical Advisor of Friends-International. * By 10th of every month, finance staff distribute financial reports to all relevant project managers. Donor financial reports are prepared and sent in accordance with donors contract deadlines. * The business financial report is distributed to all relevant project managers and management by 10th every month. * MS annual external global audit report was issued by 31stMarch 2014 by KPMG. Project Audits took place was required by individual donors such as European Union and Dan Church Aid/ChristianAid. * The stock of rice, milk, harm reduction material, hygiene and HBP products were checked by the financial staff and found everything is in good order. * The brick sale and student’s tips were controlled by financial staff every month to ensure transparency and accountability.​ In addition, the finance staff carried out spot checks on expenditure vouchers. * The list of fixed assets in the register updated from financial purchasing data; the asset will be tagged. * The finance staff received ongoing technical support by Friends-International. |
| * 1. **MS regularly monitors and evaluates its programs to ensure they are effective best practice programs** | **Monitoring and Evaluation:**   * Programs are monitored on an on-going basis to ensure best practice service delivery * Data collection tools and guidebook will update according to new structure and activities * Build capacity of PMs and specialist in monitoring, reporting and improve capacity for data analysis * Carry out annual evaluation of selected projects report + recommendations (micro-enterprise, participation/ peer educators, reintegration/ foster care) * Support evaluation from beneficiaries (TH, Green House, Club Friends) * Reports sent to donor and government on time * Research and project evaluations will conduct based on donor requirement. | **Monitoring and Evaluation:**   * The M& E team collected data regularly in each zone and monitored the team to make sure they understand the data collection forms and keep the data secure. * The monthly planning and reporting frame in Andong and ChbarAmpov zone was created and implemented according to new Mith Samlanh’s structure. * Mith Samlanh staff from five projects (transitional home, reintegration, FriendsSocial business, Green House and Education) received refresher training on daily and monthly data collection. * The 1st Quarterly Survey of Child Protection at TH, 1st Quarterly Monitoring with ChildSafe member and drug snapshot survey 2013 was conducted by Mith Samlanh specialists and analyzed by M&E team and the results of these surveys sent to all relevant team for improving the efficiency of the projects. * ​This quarter, Mith Samlanh submitted narrative reports to the following donors: ACTED/PSF,[DanChurchAid/ChristianAid](http://www.cra.com.kh/jobs/jobdetails.aspx?detailid=002F0324), European Union, Friends-Deutschland,Give2Asia, Planet Wheeler, Smile Together Foundation, SIPAR/AFD, Riverview Foundation, USAID and World Childhood Foundation, in addition togovernment partners based on their requirements. * Thelist of research and project evaluations was compiled and sent to all relevant teams. |
| 1. **Social Services** Program provides good practice protection, empowerment, education, training, employment and reintegration services to 15,000 children/youth and caretakers a year | | |
| * 1. **Best practice outreach programs are implemented in Central Phnom Penh and in communities on the outskirts** | **GLOBAL**:  **Protection:*Outreach, DIC and ChildSafe***   * 1,005,000 outreach services * 8,200 children/youth in outreach * 4,800 caretaker/adults in outreach * 150 referred to Vocational Training center and 20 place in to job. * 100 referred to Educational Center * 150 referred to detox (Green House) * 330 individuals receive legal document support (birth certificate, ID card,residential book, family book and ID poor) * 190 children/youth referredfrom (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 800 ChildSafe Members and ChildSafe Community | ***Drop In Center (DIC)*** *is a safe place providing targeted services to a defined target group without appointment, formal registration process or referral. Services provided in DIC and on outreach include lifeskills, medical, non formal education (NFE), recreational etc.*  ***Life skills topics include:*** *reproductive health, HIV/AIDS, STDS, drugs, hygiene, nutrition, life planning, street safety education, early childhood care, child rights, safe migration​ andimportance of education.*  **GLOBAL**:  **Protection:*Outreach, DIC and ChildSafe***   * 265,474 (F: 103,764) outreach services * 5,313(F: 2,132) children/youth in outreach * 2,685 (F: 1,460) caretakers/adults in outreach * 16(F:07) referred to Vocational Training center​ and 02 youth place in to job * 69(F:28) referred to Educational Center * 26 (F:02) referred to detox (Green House) * 122 (F:51) individuals receivedlegal document support(birth certificate, ID card,residential book and ID poor) * 31 (F:09) children/youth referredfrom (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 736 (F: 171) ChildSafe Members including 228 (F: 169) ChildSafe community   **Special event/ remarks:**   * Participated in a NGO partnership meetingat SangkatKhmuonh and Svay Pak on 17thJanuary 2014. * Participated in a Technical Meeting on social protection services and child labor at the office of the Council of Ministry on 11thFebruary 2014. * Participated in a workshop on partnership strengthening between Phnom Penh administration and civil society to develop poor communities in Phnom Penh at Phnom Penh Municipality on 18th March 2014. * Conducted assessment of areas and target groups in Phnom Penh in order to update MS mapping and work with new target groups especially sex workers, construction workers, car washing, out of school, out of job, etc. * Participated in the National Seminar on Parenting on 21stMarch 2014. |
| **Riverside zone:**  **Protection:*Outreach, DIC and ChildSafe***   * 200,000 outreach services * 1,500 children/youth in outreach * 750 caretakers/adults in outreach * 150 individuals receive legal document support ( birth certificate, ID card,residential book, family book and ID poor) * 70 children/youth referredfrom (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 300 ChildSafe Members and ChildSafe community | **Riverside Zone**: Outreach work and one DIC are operational with 09 (F: 05)staff and located # 33E0+E1, Street 136, SangkatPhsarThmey III, Khan Daun Penh.  **Protection:*Outreach, DIC and ChildSafe***   * 48,159(F:26,492) outreach services * 1,156 (F: 536) children/youth in outreach * 474 (F: 226) caretakers/adults in outreach * 71(F:33) individuals received legal document support (birth certificate, ID card,residential book and ID poor)​ since 1st January 2014. * 9(F:3) children/youth referredfrom (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 296 (F: 48) ChildSafe Members including 57 (F: 47) ChildSafe Community Members are active.   **Special event/ remarks:**   * On 03rd January 2014 Riverside team held an official opening event andMonks blessing ceremony to open the new Drop in Center, located at Street 136, SangkatPhsarThmey III,KhanDaun Penh. |
| **Olympic zone:**  **Protection:*Outreach, DIC and ChildSafe***   * 200,000 outreach services * 1,500children/youth in outreach * 700 caretakers/adults in outreach * 100 individuals receive legal document support (birth certificate, ID card,residential book, family book and ID poor)​ * 60 children/youth referredfrom (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 200 ChildSafe Members and ChildSafe Community | **Olympic Zone:** Outreach work is operational with 12 (F: 04) staff working directly on the streets and in communities. For the short term the team is working fromRiverside DICwhile they are looking for a new Drop In Center.  **Protection:*Outreach, DIC and ChildSafe***   * 70,572 (F:26,198) outreach services * 1,043 (F: 379) children/youth in outreach * 257(F: 143) caretakers/adults in outreach * 06individuals received legal documentsupport (birth certificate, ID card,residential book and ID poor) since 1st January 2014. * 02 boy children/youth referredfrom (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 204 (F: 31) ChildSafe Members including 62 (F: 31) ChildSafe Community Members are active.   **Special event/ remarks:**   * The Olympic Team Leader participated meeting on partnership working in Communities at Khan PrampiMakara on 21st January 2014. * The Olympic Team Leader participated in the monthly Phnom Penh Municipal board councilmeeting about March Monthly Progress Report and next quarterly work plan at Municipality on 21st March 2014. |
| **Andong Community:**  Andongprogramis providing outreach services, protection, youth empowerment, education and employment.  **Protection:*Community Outreach and ChildSafe***   * 50,000 outreach services * 1,000 children/youth in outreach * 1,000 caretakers/adults in outreach * 30 individuals receive legal document support (birth certificate, ID card,residential book, family book and ID poor) * 10 children/youth referral from (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 120 ChildSafe Members and ChildSafe Community | **Andong Community:**  Andongprogramis located in SangkatPorSenChey and is implemented by 14 (F: 04) staff. Various outreach andprotection servicesare provided including life skills, medical, non formal education, recreational.  **Protection: Community *Outreach and ChildSafe***   * 16,757 (F:7,708) outreach services * 440 (F:175) children/youth in outreach * 223 (F:140) caretakers/adults in outreach * 04 (F:02) individuals receivedlegal documentsupport (birth certificate, ID card,residential book, family book and ID poor)since 1st January 2014. * 104 (F: 55) ChildSafe Members including 69 (F: 55) Child Safe Community Members are active. |
| **ChbarAmpov Community:**  **ChbarAmpov Program**is providing outreach services, protection, youth empowerment, education and employment.  **Protection:*Community Outreach ,DIC and ChildSafe***   * 150,000 outreach services * 2,500 children/youth in outreach * 2,000 caretakers/adults in outreach * 50 individuals receive legal document (birth certificate, ID card,residential book, family book and ID poor) * 50 children/youth referral from (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 150 ChildSafe Members and ChildSafe Community | **ChbarAmpov Community:**  **ChbarAmpov Program**is located in Khan Meanchey and is implemented by 13 (F: 07) staff. Various outreach and protection servicesare provided including lifeskills, medical, non formal education, recreational.  **Protection: Community *Outreach, DIC and ChildSafe***   * 33,329(F:14,616) outreach services * 1,877(F:835) children/youth in outreach * 1,622(F:871) caretakers/adults in outreach * 36(F:16) individuals received legal documentsupport( birth certificate, ID card,residential book, family book and ID poor ) since 1st January 2014. * 20(F:6) children/youth referredfrom (DoSVY, NGOs, 3PCs Partner, Police and CCWC) * 132(F: 39) ChildSafe Members including 40(F:38) ChildSafe Community Members are active. |
| **Mobile Drug Center**is providing services in 3 ,ain locationsaround Phnom Penh   * 100,000 services * 700 children/youth * 50 referred to detoxification | **Mobile Drug Center**is providing services in 3 main locations around Phnom Penh   * 28,785 (F: 1,760) services provided * 385 (F: 56) children/youth met since 1st January 2014 * 17 children/youth referred to detoxification center since 1st January 2014. * 05 individual receive legal documents (birth certificate, ID card,residential book and ID poor) since 1st January 2014. |
| **Mobile Youth Center** (Wise Bird) is providing services in 3 main locations around Phnom Penh   * 100,000 outreach services * 800 children and youth * 350 caretakers/ adults | **Mobile Youth Center** (Wise Bird) is providing services in 3 main locationsaround Phnom Penh   * 25,647 (F: 9,735) services provided * 412 (F: 151) children/youth met since 1st January 2014 * 109 (F: 80) caretakers/adults met since 1st January 2014   **Special event/ remarks:**   * This quarter,3 special community events were organized with 497 (F: 461) participants. The events covered different topics related to health, protection against HIV/AIDS and gender equality. |
| **Diversion**   * 5 police stations in Phnom Penh are involved in the diversion system * 20 children/youth referred from police and authority to MS through diversion system | **Diversion**   * 5 police stations in Khan DaunPehn have been informed about the pilot diversion program and are willing to collaborate pending approval at higher level (MoU with municipality)   **Special event/remarks:**   * MS staff participated in training on children in conflict with the law and diversion project with Legal Aid of Cambodia on 28th-29th January 2014. * Participated in a meeting on draft of juvenile justice law at MoSVY on 04th February 2014. * Shared information about pilot diversion project with Licadho and other organizations working on juvenile justice issues and providing support to women and children in conflict with the law on 06th March 2014. |
| * 1. **Youth are empowered to actively participate in their communities and society** | **Global**  585Peer educators are trained and active in Phnom Penh including Training Center; Riverside, Olympic and two mobile youth centers and Community (Andong&ChbarAmpov)   * 175,000 services provided by peer educators * Number events and activities​ led by youth | **Global**  327 (F:108) Peer educators are trained and active in Phnom Penh including Training Center; Riverside, Olympic and two mobile youth centers and Community (Andong&ChbarAmpov)   * 7,883 (F:3,423) services provided by peer educators * 8 youth meetings were conducted by hired trainees and 106 sessions of fun activities and life skills were provided to the youth this quarter. |
| **Central Phnom PenhRiverside, Olympic, 2 mobile, TC**  ***Peer Educators***   * 468 active peer educators per year * 130,000 services provided by peer educators | **Central Phnom PenhRiverside, Olympic, 2 mobile, TC**  ***Peer Educators***   * 254 (F:81) active peer educators this quarter * 4,482(F:1,882) services provided by peer educators |
| **Andong Community:**  **Youth Empowerment**  ***Me & You Youth Center:***   * 40,000 services * 500 children/youth in Youth Center * 400 caretakers/adults in Youth Center   ***Peer Educators***   * 58active peer educators this month * 15,000 services provided by peer educators * Number events and activities​ led by youth | **Andong Community:**  **Youth Empowerment**  ***Me & You Youth Center:***   * 12,443 (F: 6,860) services provided such as first aid, life skills, NFE, fun activities * 309 (F: 102) children/youth in Youth Center since 1st January 2014. * 201(F: 115) caretakers/adults in Youth Center since 1st January 2014.   ***Peer Educators***   * 46(F:12) active peer educators this month * 1,439(F:658) services provided by peer educators * 6 youth meetings were conducted by hired trainee and 53 sessions of fun activities and life skills were provided to their youth this quarter.   **Special event/ remarks:**   * 05(F: 02) peer educators participated in an exchange visit with DamnokToekin Prey VengProvince on 13thMarch 2014. * 167 (F: 98) children, youth, parents and local authority representatives participated in a special event on the theme of ‘‘Gender Equality in Family and Society’’ at Me&You Center on 13th March 2014. |
| **ChbarAmpov Community:**  **Youth Empowerment**  ***Wise Youth Center:***   * 160,000 services * 1,000 children/youth in Youth Center * 500 caretakers/adults in Youth Center   ***Peer Educators***   * 59 active peer educators this month * 30,000 services provided by peer educators * Number events and activities​ led by youth | **ChbarAmpov Community:**  **Youth Empowerment**  ***Wise Youth Center:***   * 29,782(F:10,395)services provided (first aid, life skills, NFE, fun activities) * 868(F:429) children/youth in YouthCenter since 1st January 2014 * 767(F: 441) caretakers/adults in Youth Center since 1st January 2014.   ***Peer Educators***   * 27(F:14) active peer educators this month * 1,962(F:883) services provided by peer educators * 2 youth meetingswere conducted by hired trainee and 53 sessions of fun activities and life skills wereprovided to their youth this quarter.   **Special event/ remarks:**   * The ChbarAmpov team held a Monks blessing ceremony to open the new Youth Center, location at address # 177, Street 371, SangkatChbarAmpov Khan Mean Chey on 02ndFebruary 2014. * 62(F: 18) participants took part in a dialogue meeting with local authorities, family and youth onSexual Reproductive Health and STDs at Wise Youth Center on 23rdMarch 2014. * 21(F: 15) peer educatorsattended refresher training on Sexual Reproductive Health at Wise Youth Center on 28thMarch 2014. * 158 (F: 95) children, youth, parents and local authority representatives participated is a special event on the theme of ‘‘Youth needto know about Life-skills’’ at Wise Youth Center on 12th February 2014. |
| * 1. **Children are supported to reintegrate into public school and remain in school as long as possible** | **Education Program Global:**   * MS is providing Non Formal Education to 280 children per year * Mith Samlanh is providing supporting class to 250 children * Preparing reintegration to public school of 500 new children per year * 1,000 children enrolled in public school through campaign * 1,550 children receive support to remain in public school per year. * 4 meetings with parents and family representatives are organized to prepare school reintegration per year. * 120 children will reintegrate directly into public school (Outreach)   **Technical support**   * Total of 90,000 Non-Formal Education services (Outreach+ Educational Center +Training Center) * 60 staff are trained on NFE activities * New NFE materials are developed and updated * Guidebooks on NFE on the streets, in center, and reintegration in public school are developed, implemented and regularly updated * Evaluation of NFE activities   **Partners**   * Develop, use and update a directory of services every year and share with all teams. * 30 partner staff are identified and trained * Public school partners are trained and supported to use Toolbox | **Education Program Global:**   * MS is providing Non Formal Education to 144 (F: 61) children since 1st January 2014. * 123 (F: 66) children attended support class after reintegration to public school since 1st January 2014. * 1 child was reintegrated into public school since 1st January 2014. * The enrollment campaign will take place in 3rd quarter. * 1,382(F: 597) children received support to remain in public school since 1st January 2014and 460 (F: 197) children stop to support because they are successfully supported by their families. * Organized a meeting with 160 (F: 128) parents to recruit parent’s representatives for 2014 at Club-Friends on 06th March 2014 as result 31 (F:27) was selected parents representative.   **Technical support**   * 34,361 (F:13,003) Non-Formal Education services were provided (Outreach+ Educational Center +Training Center) * 15 (F: 06) MS staff received training on NFE activities at Educational Centre and on the field. * 59 field visits in all zones of outreach, in community, educational center, TC to reinforce the methodology of teaching and lead them to create teaching material. * 3 new Toolbox games including a puzzle, memory game and word game were created.   **Partners**   * Compiled directory of public schools to make it easier for team for communication and follow up * 5 public schools were followed up on using the toolbox. |
| **Educational Center:**   * EC is providing Non Formal Education to 200 children per year * Preparing reintegration to public school of 150 children per year * 1,300 children receive support to remain in public school per year. * 50 children attend support class per year after reintegration to public school. * 25,000 service children follow up in public school | ***Educational Center (EC)*** *offers non- formal education activities to facilitate student’s reintegration into the public school system and provides basic education to street working children and youth​. There are five classes in the EC including kindergarten, pre-school, level 0, level 1 and 2 and support class.*   * MS Educational Center provided Non-Formal Education to 130(F: 55) children at the Education Center since 1st January 2014. * The main reintegration to public school will take place at the end of Q3. * 911 (F: 427) children received support to remain in public school in Phnom Penh including 323 (F: 135) children who MS stopped to support because they are successfully supported by their families. * 32 (F: 15) children attended support class in EC after reintegration to public school since 1st January 2014. * 2,510(F: 1,159)services of school follow up were provided to children studying in public school.   **Special event or remark:**   * EC manager participated in a meeting on Education for All at NGO Education Partnership (NEP)on 20th February 2014. |
| **Andong Community:**  ***Non Formal Education***   * 30 children access remedial class * 05 youth access literacy class * 30 caretakers participate in literacy class   ***Support Class***   * 100 children/youth at public school participate in support class   ***School Reintegration***   * 50 new children reintegrated into public school * 200 children received support to remain in public school since 1st January 2014 * 400 children enrolled in public school through campaign | **Andong Community:**  ***Non Formal Education***   * 03(F:0) children accessed remedial class since 1st January 2014 * 16(F:12)caretakers participated in literacy class since 1st January 2014   ***Support Class***   * 73(F:38) children/youth at public school participated in support class since 1st January 2014   ***School Reintegration***   * 185(F: 80) children received support to remain in public school since 1st January 2014 including 30 (F: 12) children who MS stopped to support because they are successfully supported by their families. |
| **ChbarAmpov Community:**  ***Non Formal Education***   * 50 children access remedial class * 15 youth access literacy class * 15 caretakers participate in literacy class   ***Support Class***   * 100 children/youth at public school participate in support class   ***School Reintegration***   * 100 new children reintegrated into public school * 250 children received support to remain in public school since 1st January 2014 * 300 children enrolled in public school through campaign | **ChbarAmpov Community:**  ***Non Formal Education***   * 11(F:6) children accessed remedial class since 1st January 2014 * 03(F:0) youth accessed literacy class since 1st January 2014   ***Support Class***   * 18(F:13)children/youth at public school participate in support class   ***School Reintegration***   * 117(F: 48) children received support to remain in public school since 1st January 2014 including 36 (F: 16) children who MS stopped to support because they are successfully supported by their families. |
| **Club Friends** is providing 100,000 internal and external cultural services (library, dance, sports, theater, painting, study tours and special events) to all children and youth in EC and in TC as well as children from the streets per year.   * Club Friends is open to children and youth from the streets/communities two times per week, and is providing them 20,000 life skill services | ***Club Friends*** *is a center in Mith Samlanh Education center where children and youth can practice cultural and recreational activities such as sport, drawing, painting, library, dancing and music.*   * Club Friends provided 32,011 (F: 10,947) internal and external culture services such as library, dance, sports, theater, painting, study tour and special events to all children and youth in EC and TC as well as children from the streets. * Club Friends is open to children and youth from the street/ communities twice a week, and this quarter has provided them with 6,985 (F: 1,484) life skills services.   **Special event or remark:**   * 381 (F: 247) services of children/youth participating in external sport competitions such as Walking, Jumping, Running, Iron throwing, Football, Basketball and ping pong. * 58 (F: 27) Children/Youth Performed in Quarterly Show on “20th MS Anniversary” at Mith Samlanh Center with 350 Participants on 27th March 2014. * 180 (F: 76) Children/Youth participated in building their own city out of Lego as part of the OUR CITY Festival at Mith Samlanh on 21 January 2014. * 30 (F: 18) Children/Youth participated in a workshop on arts and music with Bloco Malagasy group at Mith Samlanh on 11th March 2014. * 45 (F: 19) children and youth were accompanied to visit CCF on 17th Jan2014 and 21st March 2014. * 698 (F:263) services of Children/youth participating in drawing and painting the front gate at Mith Samlanh |
| * 1. **Youth are supported to access vocational training and employment** | **Vocational Training and Youth Employment Global**  *Vocational Training is provided in 8 different vocational training workshops in the main MS TC and in 2 new workshops to be located in the communities to be opened during 2014.*   * Vocational training is provided to 620 youth per year * 40 youth are placed in apprenticeship   **Job Placement**   * A total of 180 youth supported for employment in Phnom Penh and Provinces per year * 100 youth are placed in gainful employment in Phnom Penh and Provinces * 30 youth are placed in gainful self-employment in Phnom Penh and Provinces * 40youth supported for direct employment in Phnom Penh and Provinces * 10 youth find the job by themselves in Phnom Penh   **Technical support**   * 20 case managers in TC and other zones are trained and support on job placement and 20 receive refresher training * Evaluation of job placement activities * Guidebook on Vocational Training, Apprenticeship and Job Placement are developed, implemented and regularly updated   **Partners**   * Create and update job directory and share with case managers | ***VT and Youth Employment Global***  *VT is currently provided in 8 VT workshops in the MS training center. A pilot apprenticeship project has also started in ChbarAmpov community.*   * Vocational training is provided to 308 (F: 87) youth​​ since 01stJanuary 2014. * 22 (F:05) youth have been placed in apprenticeship as part of pilot apprenticeship training project   **Job Placement**   * 31 (F: 07) youth were reintegrated into employment in Phnom Penh and Provinces, including: * 21 (F: 03) youth were placed in gainful employment in Phnom Penh and Provinces. * 04 (F: 0) youth were placed in gainful self-employment in Phnom Penh and Provinces. * 04 (F: 03) youth were placed immediately in a job in Phnom Penh. * 02 (F: 01) youth found a job by themselves in Phnom Penh and Provinces.   **Technical support**   * 16 (F:07) MS staff received training on Job Placement at Friends-International on 10thJanuary 2014 * Conducted market study for screen printing * Job placement guidebook is finalized in English and will be translated into Khmer next quarter.   **Partners**   * 193 private shops/NGO partners have been included in the job directory and shared with case managers. * Met withThe Cambodian Children Against Starvation and ViolenceAssociation (CCASVA) for apprenticeship. |
| **Vocational Training Centre** (workshops and businesses) are providing arrange of different vocational skills to 600 children per year (with a minimum of 30% of girls), and supports them for placement into employment or self-employment   * 500 youth receiving vocational training graduated after completing at least one level from TC per year. * 150,000 services (education, life skills, computer and Treatment) are provided to youth in vocational training center. * By 2017, the dropout rate of vocational training has decrease 10 % (baseline in 2012 = 18%) \* * 130 youth receive support for Placement into Employment or self-employment per year; including, youth supported to live independently. * 85 % of youth remaining into employment or in self employment 6 months after placement. | ***Vocational Training Centre (TC)*** *provides quality vocational training leading to viable employment options for youth. Mith Samlanh has 8 different vocational skills at the TC.*   * Vocational Training Centre provided vocational skills training to 307 (F: 87) youth at the TC since 1st January 2014. * 21 (F: 05) youth receiving vocational training graduated after completing at least one level from the Training Center since 1st January 2014. * 52,679 (F: 16,277) services (education, life skills, computer, medical treatment, work readiness and literacy) were provided to youth in the vocational training center. * 17 (F: 2) youth (equivalent to 5.5%) dropped out of vocational training since 1st January 2014 (and have not come back at the end of the reporting period)\*. * 24 (F: 4) youth received support for placement into employment and 18 (F: 3) youth were supported to live independently in Phnom Penh since 1stJanuary 2014. * 85% of youth placed are remaining in employment or in self employment 6 months after placement.   **Special event or remark:**   * 17 (F: 13) students and staff participated in a festival entitled Amazing Acoustic Picnic to raise funds at Mith Samlanh on 08th February 2014. * The Vocational Training Center Manager participated in a meeting on "Cambodian Tourism Lecturers Establishment and Implementation of 144 ASEAN Toolboxes of Hotel Services" on 21st February 2014 * The Vocational Training Center Manager participated in a Workshop for Industrial Liaison Units (ILUs) on Developing a National Communication and Marketing Plan (2014-2016) Organized by Ministry of Labour and Vocational Training in Collaborated with ADB on 04th March​​ 2014. * The Vocational Training Center Manager participated in two meetings at Save the Children office in March to discuss Technical and Vocational Education and Training​ (TVET) at urban and provincial levels, and present MS’s approach to ``Hard and Soft Skills`` to 26 participants of government and NGOs. |
| **ANDONG COMMUNITY​:**  **Employment**  ***Vocational Training Workshop***   * 05 youth participated in VT (sewing workshop)   ***Job Placement***   * 05 students reintegrated into employment (job, self-employment, find a job by themselves and direct job)   ***Apprenticeship***   * 5 youth placed in apprenticeship | **ANDONG COMMUNITY​:**  **Employment**  ***Vocational Training Workshop***   * 01 (F:0) youth attended VT at the screen printing workshop since 1st January 2014.   ***Job Placement***   * 02 (F: 01) students were reintegrated directly into employment since 1st January 2014. |
| **CHBAR AMPOV COMMUNITY:**  **Employment**  ***Vocational Training Workshop***   * 15 youth participated in VT (motor workshop)   ***Job Placement***   * 15 students reintegrated into employment (job, self-employment, find a job by themselves and direct job)   ***Apprenticeship***   * 35 youth placed in apprenticeship | **CHBAR AMPOV COMMUNITY:**  **Employment**  ***Vocational Training Workshop***   * The new motorbike workshop will open in Takhmao inthe 2nd quarter.   ***Job Placement***   * 01 student was reintegrated directly into employment since 1st January 2014.   ***Apprenticeship***   * 22 (F: 05) youth were placed in apprenticeshipsince 1st January 2014. |
| * 1. **Children and youth are provided with safe temporary shelter and supported to reintegrate into their family** | ***Transitional Home/Independent living***   * 3 Transitional Homes are providing safe accommodation to a maximum of 500 children per year * 24,000 services (outings, child participation, family visits, child protection and medical), including 9,000 medical services are provided to children/youth in THs. * 350 children from the street and the TH are joining Camp SabaySabay activities in Kampong Speu Province per year * Child participation is ensured with general meetings every week, elections and suggestion boxes in all THs. * 15 new youth will support to live independently in a group setting during their studies at Mith Samlanh per year | ***Transitional Home*** *is a safe temporary residence for children and youth requiring accommodation during their studies or until their family situation stabilizes.*   * 3 Transitional Homes located in SangkatTuekLak, TumnobTuek 3 and Toul​Svay Prey 1 provided safe accommodation to 214 (F: 54 ) children and youth since 1st January 2014. * 5,232 (F: 407) services (outings, child participation, family visits, child protection and medical) including 2,372 (F: 372) medical services were provided to children/youth in all Transitional Homes. * 38 (F: 03) children/youth from the Transitional Home joined Camp SabaySabay activities in Kampong Speu Province since 1st January 2014. * All children participated in general meetings every week and opened the suggestion boxes twice a month in each TH.   **Special event or remark:**   * 92 (F: 30) children/youth were accompanied to watch the Amazeing Historical story at Koh​ Pich theater on 08th-09th February 2014. * New material was provided for each centerincluding cupboards and cabinets. |
|  |  |
| ***Family Reintegration Phnom Penh and Province***   * 800 caretaker in province will receive services (life skills, legal support and referral ) per year. * 80 children are supported to reintegrate to their family, extended family and living independent in their province per year. * 80 children are supported to reintegrate to their family, extended family in their Phnom Penh per year. * 80 children are supported to reintegrate public school in their province per year. * 270 children are supported to remain in public school in their province per year. * 10 new youth placed in employment or in their own business in their province per year * 100 youth are followed up to remain in employment or start their own business in their province per year. * 15 street living families are supported to return to their homeland per year. * 10 families received training and support for small business in their province and 40 children are benefiting from it per year. * 20 individual receive legal document (birth certificate, ID card,residential book, family book and ID poor) in their province per year.   **Technical support**   * Guidebook/SOPs on reintegration and foster care are adapted, translated and implemented in the team by the end of year 2014.   **Partners**   * Collaboration with government and NGOs partners is developed through meetings and training. | ***Family Reintegration Phnom Penh and Province***   * 270 (F: 170) caretakers in the provincesreceived services (life skills, legal support and referral ) since 1st January 2014 * 08 (F: 02) children were supported to reintegrate to their family, extended family and independent living in their province since 1st January 2014. * 14 (F: 03) children were supported to reintegrate to their family, extended family in their Phnom Penh since 1st January 2014. * 1 new child is supported to reintegrate public school in their province since 1st January 2014. * 119 (F: 54) children are supported to remain in public school in their province since 1st January 2014 and 71(F: 43) children stop to support because they are successfully supported by their families. * 20 (F:03) youth including new 02 placed in employment or in their own business in their province since 1st January 2014 * 20 (03) youth are followed up to remain in employment or start their own business in their province per year. * 1 family received training and supported for small business in their province and 03 (F:03) children are benefiting from it since 1st January 2014 * 01 youth was supported to receive ID card since 1st January 2014.   **Technical support**   * 60% of the SOPs on family reintegration were completed by FI Technical Advisor and the Foster care on the field assesses processing.   **Partners**   * Continuing to collaborate with Commune Council for Women and Children (CCWC), DoSVY and other NGO partners on reintegration tasks such as family tracing, assessment, family planning, and reintegration and follow up in 25 Provinces/City. |
| ***Foster Care***   * 10 new children are supported to integrate a foster care family per year. * 4 foster care committee meetings are organized per year. | ***Foster Care***   * 10children in foster care are provided with ongoing follow up but no new children were place in to foster care in this quarter. * The department of social welfare of Ministry of Social Affairs, Veterans and Youth has supported Mith Samlanh on foster care. * 1 foster care committee meeting was conducted at MoSVY to discuss the new strategy plan and draft Term of Reference of foster care committee and solution to material supply in the committee on 27th February 2014. |
| **Reintegration from prison**   * 5,000 life skill services provided in CC1 and CC2 prisons in Phnom Penh * 200 prisoners provided with life skill education pre-release | **Reintegration from prison**   * 869(F:197) life skill education services were provided to prisoners in CC1 and CC2 * 133(F:41) prisoners were reached since 1st January 2014 * 24 (F: 03) prisoners have been reintegrated to Training Center and family. |
| * 1. **Independent families are able to earn an income and support their children** | **Global:**  **Home Based Production**   * 135 caretakers including 69 new caretakers attend training and participate in Home Based Production and 540 children are benefiting from it per year   **Micro Enterprise**   * Micro Enterprise team is providing training and support to 140 families including 65 new to run their own micro enterprise to improve their revenue and 560 children are benefiting from it.   **Production Center: (Andong and FI factory)**   * 15 caretakers are supported for employment in Andong Screen Printing and FI factory   **Technical support**   * Finalize/adapt HBP and ME guidebooks from FI   **Partners**   * Collaboration with NGOs partners and private is developed through training, product selling and exhibition or other event. | **Global:**  **Home Based Production**   * 75 caretakers including 09 new are participating in Home Based production and 246 (F: 106) children are benefiting from it.   **Micro Enterprise**   * Micro Enterprise team provided training and support to 78 caretakers including 03 new to start their own business and improve their revenue with 271 (F: 120) children benefiting through micro enterprise.   **Production Center: (Andong and FI factory*)***   * 04 caretakers are supported for employment in Andong Screen Printing and FI factory since 1st January 2014   **Technical support**   * HBP and Micro Enterprise Guidebook are in the draft and HBP Beneficiary Evaluation has conducted but the evaluation report is in draft process. * Marketing campaigns were developedfor Valentine’s Day and Khmer New Year. * A new form has been created to order products monthly and easily control stockand selling. * Purchased new products from beneficiariesto sell atRomdeng andFnSToulTompong shop. * The product development process has been reviewed and presented to the team.   **Partners**   * The Friend Social Business team joined 3 exhibitions to sell HBP products at various events atKohPich,[The International School of Phnom Penh](http://www.ispp.edu.kh/)​ and Cafe Sejour. |
| **Andong Community:**  ***Home Based Production:***   * 45 caretakers including 20 new attend training and participate in Home Based Production and 180 children are benefiting from it per year * 10 caretakers doing screen printing in Production Center   ***Micro Enterprise***   * 25 caretakers including 18 new are receiving micro business training and support to start their own micro business to improve their revenue and 100 children are benefiting from it per year.   ***Apprenticeship***   * 5 caretakers placed in apprenticeship in this year | **Andong Community:**  ***Home Based Production:***   * 26 caretakers including 1 new caretaker attended training and are participating in Home Based Production and 91 (F: 35) children are benefiting since 1st January 2014. * 04 caretakers working on screen printing in the Production Center since 1st January 2014   ***Micro Enterprise***   * 09 caretakers including 02 new caretakers are receiving micro business training and support to start their own micro business to improve their revenue and 38 (F: 18) children are benefiting since 1st January 2014. |
| **ChbarAmpov Community:**  ***Home Based Production:***   * 35 caretakers including 26 new attend training and participating in Home Based Production and140 children are benefiting from it per year   ***Micro Enterprise***   * 28 caretakers including 20 new are receiving micro business training and support to start their own micro business to improve their revenue and 120 children are benefiting from it per year.   ***Apprenticeship***   * 10 caretakers placed in apprenticeship in this year | **ChbarAmpov Community:**  ***Home Based Production:***   * 13 caretakers including 4 new caretakers attended training and are participating in Home Based Production and 44(F: 24) children are benefiting since 1st January 2014.   ***Micro Enterprise***   * 08 (F: 06) caretakers including 00 new caretakers are receiving micro business training and support to start their own micro business to improve their revenue and 28 (F: 15) children are benefiting since 1st January 2014. |
| * 1. **With the support of FSB, MS is 60% sustainable:** | Sustainability is 60%   * 100 % of 8 vocational training skills at Vocational Training center will generate income $ 55,000 by the end of 2014. * 2 vocational training restaurants are increasing income by 10%, making $1,337,261 income 210,952 net income per year * Friends Restaurant: $750,818 income $155,130 net income * Romdeng $586,443 income $55,822 net income * **Nailbar** located inside the Friends ‘N’ stuff shop on St 13 income 14,042 increases of 5% per year. * **Sales** from HBP at FNS St13, Tool Tompong, Romdeng are making $ 307,000 income * SoPs for customer service, shop layout, merchandising for shops and service SoPs for restaurants adapted from FI * **MS products** (Cook Book Best of Friends) makes a gross income of $36,000 per year (increase 2%), net income $25,000. | Sustainability is 44% this quarter.   * 100% of 8 vocational training skills at Vocational Training center generated income this quarter, generating a total of $13,576.20. * 2 vocational training restaurants made $ 498,168.26 total income with a net income of $125,681.17 so far this year: * Friends Restaurant: $ 284,620.75 income; net income $83,803.27 * Romdeng: $ 213,546.51 income; net income $ 41,877.90 * **Nailbar**located inside the Friends ‘N’ stuff shop on St 13 next to The Friends- Restaurant made $ 3,884.60 income and net income $ 385.59 * **Sales** from HBP at FNS st13, FNS ToulTompong and FNS Romdeng made $125,569.86 income and net income $59,812.15 * Revised training schedule and curriculum of Level 1 hospitality students for two months period * The Moto curriculum was updated and translated in Khnmer version. * SoPsfor hair cut class and nail bar are drafted * SoPs for Moto class, Health/injury and Safety workshop were approved by program director and implemented by team * **MS products** (Cook Book Best of Friends) made an income of $7,767.20 and net income $7,767.20 |
| 1. **Six Specialized teams are providing support to Programs in 2014** | | |
| * 1. **Child Protection Specialist** | **Impact on Children:**   * 100 cases of abuse report form completed.   **MER**   * Evaluation of Child protection policies in all DIC, EC, TC and all THs. * Organize quarterly survey of children staying in THs, Green House and TC (Restaurants)   **Technical support**   * 100% staff are trained and receive refresher training on Child Protection policies * Child Representative election are organized every 6 months/year   **Tools**   * Update and implement Child Protection policies tools * Child Protection policies are displayed in all centers * Develop child participation guidebook (in centre, in families, in communities, in society) and guidelines for elections of student representatives * Ensure all tools are available in every center | **Impact on Children:**   * 51 (F: 16) abuse cases report forms were completed; all cases were related to physical abuse.   **MER**   * This quarter, surveys about Mith Samlanh services, their needs and problems were conducted with22 (F:06) children/youth staying in 3 Transitional Homes and the results were reported to relevant project managers to put into their work plan and take action based on the recommendations.   **Technical support**   * 82 monitoring and technical support visits were conducted by the Child Protection Specialist at Training Center, Educational Center, Drop in Centers, outreach and THs to reinforce implementation of child protection policy and ensure security of children.   **Tools**   * The child protection policy, Internal Regulations, materials and Reporting System of child protection are posted in all centers.   **Partners**   * Organized for 02 (F: 01) children to participate in a workshop on strengthening child rights and child participation in ASEAN communities at NGO CRC on 10th February 2014. * Participated in a meeting on how to organize international children’s day and select the topic for this year’s event at MoSVY on 25th February 2014. * Participated in a meeting to discuss international children’s day and conduct a functional review of NGO Coalition on the rights of the child at NGO CRC on 20th March 2014. * Participated in a workshop on draft guidelines on the referral of child victims of human trafficking and sexual exploitation on 28th March 2014. |
| * 1. **Medical Specialist** | **Impact on Children:**   * 100,000 total consultations and first aid carried out to children/youth including 30,000 DU/IDUs services * 800 referral services to hospitals * 10 children/youth treated at hospital for HIV/AIDS since 1st January 2014 * 30 caretakers/adults treated at hospital for HIV/AIDS since 1st January 2014 * 300 service of consultation/treatment to youth for STDs * 400 service of caretakers/adult for STDs * 350 referrals to the Voluntary Confidential Counseling and Testing (VCCT) per year * 300 children and youth affected and infected by HIV/AIDS will receive social support from Mith Samlanh. * 50 children/youth will receive ARV & OI treatment per year * 180 Parents infected with HIV/AIDS received social support at MS and are receiving ARV and OI treatment per year   **MER**   * Evaluation of medical care in all projects   **Technical support**   * All medical staff will receive regular trainings * 50 staff (case managers & Social work) are trained on basic dental and first aid * Improve collaboration between medical staff and case managers * Review, monitor and order medical materials based on the needs of the teams   **Tools**   * Guidebooks are developed, implemented and regularly updated | **Impact on Children:**   * 33,733 (F: 13,356) consultations and first aid services including 10,378 (F: 2,640) consultations/treatment for Children/ youth drug users. * 206 (F:92) referral services to hospital * 05 (F: 01) children/youth accessed treatment at hospital for HIV/AIDS since​​ 1st January 2014. * 15 (F: 06) caretakers/adults accessed treatment at hospital for HIV/AIDS since 1st January 2014 * 82 (F:36) consultations/treatment services provided to youth for STDs * 126 (F: 95) consultations/treatment services provided to caretakers/adults for STDs. * 116 (F: 36) referrals to the Voluntary Confidential Counseling and Testing (VCCT) since 1st January 2014. * 256 (F: 117) Children/ Youth affected and infected by HIV/AIDS accessed social services since 1st January 2014. * 34 (F: 20) Children /youth received ART and OI treatment since 1stJanuary 2014. * 132 (F: 87) parents infected with HIV/AIDS received social support at Mith Samlanh and are receiving ART and OI since 1st January 2014.   **MER**   * Through regular visits and monitoring from medical specialist, all the clinics have good hygiene and the rooms are comfortable. The child observation form was completed and medicine stock is well organized. * 127 (F: 33) children/youth received medical checkup before studies in Mith Samlanhcenter and placement into employment or self employment.   **Technical support**   * 3 cases were provided with emotional support, treatment and solution from case manager and team leader with support from medical specialist * 24 fields visits to allzones of outreach, Green House, Mobile Drop in Center, Transitional Home, toassisti case managers and team leaders and support children, youth and families health. * 30 (F: 08) MS staff received Hepatitis B vaccine (second vaccine). * 35 (F: 18) TH staff and home based caretakers in Andong received explanation on First Aid guidelines.   **Tools**   * Reviewed draft Hygiene, Nutrition, Health Book for Friends-International and SIPAR.   **Partners**   * Collaborated with doctors at Kean Klang Rehabilitation Center,  Calmette Hospital, Kunthabopha hospital, Khmer-Soviet Friendship Hospital, Municipal referral, National Centerfor Dermatology, STDs, and HIV/AIDs, CheuyChomnas Hospital in order to support children and youth pro bono. * Participated in Medicam and Phnom Penh Municipal Health Department Monthly meeting regarding collaboration with other medical NGO partners. * Participated in conference on Hospital Diet Management at National Pediatric Hospital on 20th March 2014. * 121 (F: 39) children of Educational Centerwere supported to access treatment and dental health care from One 2 One NGO at [PreahKetMealea Hospital.](http://www.agoda.com/asia/cambodia/phnom_penh/attractions/hotels_near_preah_ket_mealea_hospital.html)   **Special Event or remark:**   * This quarter, The Khmer-Friendship hospital continues to discount 20% and Phnom Penh Municipal Hospital discount 10% for Mith Samlanh beneficiaries and ​​theagreementbetweenMithSamlanhandCheyChumneas Referral Hospital for patients is in process. |
| * 1. **Case Management Specialist** | **Impact on children:**  Active cases:   * 5,000 individual cases * 550 family cases * 21 community cases   New cases:   * 700 individual cases * 120 family cases * 4 community cases   Closed cases:   * 300 individuals cases * 50 families cases * 2 community cases   **MER**   * Monitoring and data collection system are in line with Friends Programs standards indicators for case management system * Evaluation of Case Management system will conduct once per year * Support and roll out of case management database   **Technical support**   * 80 staff are trained on Case management system​ and social psychology * 50 staff are acting as Case managers * Case management meeting are organized and conduct on weekly basis with Case Manager in each zones and monthly with team leaders at Mith Samlanh office.   **Tools**   * Improve and change some part of restructure case management meeting.   **Partners**   * Develop, use and update directory of services every year and share with all teams. * 20 partner staff are identified and trained * Relationship with Government departments are effective | **Impact on children:**  Active cases this quarter:   * 2,233 individual cases * 298 family cases * 23 communities cases   New cases opened this quarter:   * 209 individual cases * 20 family cases   Closed cases this quarter:   * 275 individual cases * 86 family cases   **MER**   * 55 field visits in all zones of outreach, Training Center, Education center and Transitional Home to reinforce the case management process and management of individual cases.   **Technical support**   * 34 case management meetingswere organized and conducted on a weekly basis with Case Managers in each zoneand monthly with team leaders at Mith Samlanh office to discuss challenging cases and solve the problems of children/youth. * 07 (F: 03) staff received refresher training on guidelines for handover of cases at ChbarAmpov on 18th March 2014. * 56 (F: 25) MS staff received refresher training on IPSS at Friends-International on 25th March 2014.   **Partners**   * Directory of services is being updated by Friends-International. * 03 (F: 02) Hotline and Kaliyan Mith Chom Chao staff received refresher training on IPSS at Friends-International on 25th March 2014. |
| * 1. **Drug Specialist** | **Impact on Children:**   * 200,000 clean needles/syringes distributed to youth * 120,000 services to DU/IDU per year * 150 children/youth access detoxification and rehabilitation services   **MER**   * Evaluation of activities linked with Drugs (life skills, harm reduction, detoxification) * Conduct one snapshot survey of Drug Users in Phnom Penh per year   **Technical support**   * 30 staff are trained on drug knowledge   **Tools**   * IEC on drugs are monitored and updated on an ongoing basis * Guidebooks are implemented and regularly updated   **Partners**   * Review and update directory of services every year and share with all teams * 20 staff of NGO/GO Partners are identified and trained * Relationships with Government departments are effective | **Impact on Children:**   * 65,494 clean needle/syringes distributed to youth * 34,635 harm reduction services provided this quarter. * 32 (F: 02) children/youth accessed detoxification and rehabilitation services this quarter.   **MER**   * 85 field visits were conducted in all zones/communities, Mobile Drop in Centers, Green House, Transitional Home, Training Center and Educational Center to provide technical support. * Conducted regular monthly [Needle & Syringe Program](http://www.health.vic.gov.au/aod/about/needle.htm)assessment with an average of 45 IDU in all zones in collaboration with Friends-International. * The annual drug snapshot survey 2013 has been analyzed by M&E team and the result has sent to Friends-International TA for checking. * Mith Samlanh in process of conducting assessments and developing new activities and schedules to locate more marginalized youth and hidden drug users.   **Technical support**   * 41 (F: 20) MS staff received on drug data collection at Mith Samlanh Office on 28th March 2014.   **Tools**   * Ongoing monitoring of the implementation of IEC materials for Drug Harm Reduction and Prevention with outreach team, updating as necessary. * The drug data collection tool has been completed, staff have been trained and the tool is being implemented by the relevant teams.   **Partners**   * Participated in a meeting to review the achievements of drug harm reduction with NSP program and MMT 2013 and future plan on 26th February 2014. * Participated in a meeting todesign the new Quarterly National Drug Data collection at [National Authority of Combating Drugs (NACD)](http://yp.com.kh/listings/kh53891-national-authority-of-combating-drugs-nacd)on 27th February 2014. * Participated in discussion with GF, LFA, NCHADS and FI on how to improve drug data collection and reporting at MS on 13rd March 2014. * Participated in a meeting on Drug control 2013 at NACD on 25th-26thMarch 2014. |
| **DETOX CENTER** (Green House) receive 150 clients per year   * 90,000 service * 150 children and youth have accessed detoxification treatment * 120 children and youths are referred to Educational Center and Training Center | **DETOX CENTER** (Green House) received 32 (F: 02) clients this quarter   * 24,700 services were provided this quarter * 32 (F:02) children and youth have accessed detoxification treatment * 20 (F: 01) Drug Users successfully completed formal rehabilitation, among them 09 youth who were referred to study at Mith Samlanh training center, 06 (F: 01) youth who were reintegrated into their communities and 5 who were reintegrated to [Pour un Sourired'Enfant](https://www.facebook.com/psecambodia)by the reintegration team since 1st January 2014. * 01 (F: 01) Drug User dropped out from Green House since 1st January 2014. * 04 Drug Users remain in Green House at the end of March 2014. |
| * 1. **Life Skills Specialist** | **Impact on Children:**   * 425,000 life skills services (children/youth) * 205,000 life skills services (caretakers) * 350,000 condoms distributed to youths and caretakers * 125,000 HIV/AIDS education services * 125,000 reproductive health services * 45,000 child rights services * 400 caretakers participate in Emotional Support Group (EGS) with 6,000 services per year   **MER**   * Evaluation of life skills/peer educator activities   **Technical support**   * 50 staff are trained on basic knowledge of life skills, HIV/AIDS (ARV, PMTCT, VCCT ,etc) | **Impact on Children:**   * 138,404 life skills services provided to children/youth * 61,768 life skills services provided to caretakers * 72,900 condoms distributed to youth and caretakers * 34,827 HIV/AIDS education services * 28,038 reproductive health services * 10,910 child rights services * 283 (F:156) caretakers participate in Emotional Support Group (EGS) with 687 (F: 374) services since 1st January 2014.   **MER**   * Conducted pre test on HIV/AIDS with 231 (F: 101) youth studying at Training Center, outreach and community.   **Technical support**   * 06 (F: 02) MS staff received refresher training on how to select and trainpeer educators at Andong on 25th March 2014. * Participated in regular monthly meetings with social workers and all EGS facilitators at Olympic zone to identify the challenges, solutions, feedback and sharing information or lesson learnt as well as discussing topics for EGS next meeting. As a result, the facilitators are able to learn from each other, improve their implementation and solve the problem timely to our beneficiaries.   **Partners**   * Participated in the Validation workshop on Cambodia’s 2014 Global AIDS Response Progress Reporting (GARPR) in Phnom Penh on 21st March 2014. * Participated in the Consultation workshop on “Exploring practitioners’ approaches and methodologies for empowering vulnerable youth in Cambodia” at Save the Children Office on 27th March 2014. |
| * 1. **ChildSafe Specialist** | **Impact on children:**   * 120 new ChildSafe members trained and certified per year. * 800 active ChildSafe members including ChildSafe Community Members in Phnom Penh by end 2014 * 1,500 actions taken by members to protect children   **MER**   * Evaluation of all ChildSafe member in Phnom Penh on regular basis * Develop and implement monitoring and reporting tool for CSN member   **Technical support**   * 80 staff are trained on basic knowledge of ChildSafe members * Review, monitor stock and order new materials for ChildSafe members   **Tools**   * IEC ChildSafe are monitored and updated on going * Guidebooks on ChildSafe Network is reviewed, implemented and regularly updated   **Partners**   * Use and update directory of services every year and share with all teams. * 40 staff of Partner organizations are identified and trained through Friends-International * Relationships with Government departments are effective | **Impact on children:**   * 54(F: 13) new CS members including 16(F: 12) new CS community members were trained and certified this quarter. * 736 (F: 171) ChildSafe members (189 motors, 317 (F: 2) Tuk-Tuks, 2 Taxis, and 228 (F: 169) ChildSafe community) are active since 1st January 2014. * 646 actions were taken by ChildSafe members this quarter to protect children, such as: referral to MS center, share information about ChildSafe project to client or visitors, provided information about MS services, provided number/card of ChildSafe hotline, referral to hospital and calls to ChildSafe hotline or police.   **MER**   * The​​1stChildSafe quarterly monitoring was conducted with 208 ChildSafe members by outreach staff in Phnom Penh.   **Technical support**   * 47 (F: 21) MS staff received training on ChildSafe guidebook and 7 tips, Safe migration and road safety at 4 Zones. * 52 field visits for meeting ChildSafe members and providing technical support directly to field staff at Outreach and all THs this quarter. * 29 (F: 08) new ChildSafe TukTukmembers received on the field training on ChildSafe IEC by Outreach on 20thJan – 10th/26thMarch 2013. * 257 (F: 32) ChildSafe members received ChildSafe Refresher training on Child Rights and Child protection at Friends-International.   **Tools**   * 200 shirts were printed by Home Based​​ Production team on 20th February 2014. * 420 shirts and 231 ID card, 68 display cards were provided to Outreach team on 12th /19th March 2014.   **Partners**   * Participated in Workshop on NCA- CEOP ICPN East and Southern Asia Regional Child Protection organized by National Crime Agency (NCA) on 3-4 March 2014. * Participated in a meeting on NGO network improving organised by Ecpat on 28th February 2014. |

**Approved by: Verified by: Prepared by:**

**MâpSomaya PhengSaochheng Bun Rathana**

**Program Director Monitoring and Evaluation Manager Monitoring and Evaluation Officer**